## Slide 1: Mindset in Education High level scoping document
DRAFT
Notes: This Design in Principle should describe the scope of the release or a change request.
It describes a work package.

## Slide 2: Contents
1
2
Assumptions
3
4
High-Level Scope
5
Current state – PBM process
6
Proposed change & ‘to-be’ process
Problem \ Opportunity statement
9
Document management
Appendix
Objectives & Success criteria
8
7
High-level user stories
Notes: Please track changes here

## Slide 3: Problem \ Opportunity statement
An individuals motivations, personality and cognitive outlook can be influenced by their underlying assumptions and beliefs i.e. their mindset.
According to Carol Dweck, Professor of Psychology at Stanford University, Individuals possess either a fixed mindset (in which they hold limiting beliefs that their successes are due to inherent and fixed abilities) or a growth mindset (in which they believe their abilities are not inherent but can be developed through effective learning and persistence).
An individual who adopts a growth mindset will typically attribute their achievements to tenacity and hard work and thus more likely, in spite of setbacks, to continue to work towards personal and professional goals and ultimately live a less stressful and more successful life.
Winning Scotland Foundation (WSF) mission is to empower all young people in Scotland to be ambitious, versatile, resilient with the self-belief to succeed. One way in which this is being realised is by promoting the adoption of a growth mindset within an education setting via three professional learning programmes:
Mindset Champions - A blended training course combining online, peer and face-to-face learning, culminating in a tutor-supported delivery of a classroom project
Mindset Leaders - Supporting senior school staff and educational leaders to spread mindset through their school, authority or region
Mindset in the Curriculum - Supporting the development of growth mindset into areas like numeracy, literacy and science.
WSF are working with classroom teachers and education leadership in hundreds of schools across dozens of local authorities to create a growth mindset culture which is demonstrating the development of resilience and perseverance in pupils as well as changing the teachers perceptions of their pupils abilities.
WSF have engaged the Scottish Tech Army (STA) to support this initiative as there is a need to process and report on a large volume of qualitative and quantitative data that is collected throughout the learning programmes. There is currently limited analytics capability and the current solution is inefficient, manual, and does little to support the quality data analytics required to highlight and evidence the impact of Growth Mindset in an education setting.
3
Notes: Please track changes here

## Slide 4: Objectives
4
ID | Description
SC01 | Qualitative and quantitative data can be collected, processed and reported on by the WSF team
SC02 | The WSF team are able to perform basic exploratory data analysis to formulate and support hypotheses
SC03 | Results from data analysis can be shared externally
SC04 | The WSF team are able to track: Impact on pupils Levels of attainment in Maths / Numeracy (quantitative) Levels of attainment in Literacy (quantitative) Levels of attainment in Science (quantitative) Resilience (qualitative) Confidence (qualitative) Attitude to leaning (qualitative) Mental wellbeing (qualitative) Impact on teachers Attainment scores (quantitative) Changes in pedagogy (qualitative) Attitudes and expectations towards young people (qualitative) Attitude and expectations towards colleagues (qualitative) Attitude towards implementing change (qualitative)
The project has two key objectives:
Define and implement a system to support data management and analytics
Evaluate the processes in which data is collected and managed to support the required analytics
Success criteria
Notes:
Primary focus is on the ability to track teachers
Quantitative data will not always be available and will captured only when possible
Questionnaire will be issued before and after engagement to establish a benchmark for comparative analysis
Notes: Please track changes here

## Slide 5
Assumptions
Assumption | Validated
MS SharePoint will be used for the storage of content | Yes
WSF staff will be responsible for loading data into the analytics platform | Yes
There will be manual transformation of data so that it can be loaded into the solution in a structured way. In time, data will be collected in such a was as to minimise this effort | Yes
WSF will not always have access to pupil and teacher attainment data in order to perform the required quantitative analysis. | Yes
There will be no PII held on the analytics platform | Yes
Data will be stored in such a way as to maintain the various relational entities i.e. pupil, teacher, school | Yes
A commercial off the shelf (COTS) product is available to support the reporting and analytics requirements which can be adapted to align to standard out of the box functionality | No
The system will be cloud hosted | No
WSF will be responsible for implementation, licensing and ongoing running costs | Yes
Training will be provided free of charge by STA so long as appropriate resources can be identified to support. If no resources are identified a 3rd party may be required to support training and WSF will be responsible for any costs incurred | No
At the time of producing this document a number of assumptions exist. These assumptions have been listed below and should be validated as early as possible
Notes: Please track changes here

## Slide 6: High-Level Scope
In Scope | 
People | Participating teachers
 | Participating school leaders
 | Pupils from participating schools
 | WSF staff
Process | Data collection
 | Data processing
 | Analytics and reporting
Technology | Implementation of a data analytics solution
 | Implementation of reporting solution
 | Definition of queries and reports to support the analysis outlined in the success criteria
Out of Scope | 
Technology | Generation of specific studies or hypotheses
 | Secure submission of content
 | Local storage of content
 | Automated ingestion of submitted data into the analytics platform
 | Definitions of specific data visualisations
 | Definition of complex queries and reports other than those required to support the analysis outlined in the success criteria
 | Implementation of a content management platform for data submission
Notes: Please track changes here

## Slide 7
Current State
Programme participants submit content during and on completion of project via an online portal
Content is saved to document repository
Content is downloaded, extracted and transformed manually. Key data entered into a local spreadsheet
Spreadsheet entries form the basis of manual data analysis
Teacher
School Leader
Submitted data
Submitted data
Winning Scotland Foundation
School A
School B
WSF Team member
MS SharePoint?
1
1
2
3
4
Notes: Please track changes here

## Slide 8
Proposed change & ‘to-be’ process
Data submission
Data transformation
Data load
Data processing
Analytics & reporting
 | Data submission | Data transformation | Data load | Data processing | Analytics & reporting
Current state | Submitted through online portal hosted by Moodle | Data is manually assessed and summarised. Key words are identified | Transformed data is manually keyed into a spreadsheet | Excel used for basic analysis | None
Interim state | As above but participants will be asked to complete standard templates for comparative analysis | As above | Transformed data is manually keyed into a spreadsheet. Spreadsheet is connected to Analytics Tool | Analytics Tool will be used for exploratory, univariate and multivariate data analysis | Analytics tool will generate user defined visualisations to support the output of the exploratory analysis
Target state | Online form hosted on WSF platform to capture pre and post engagement questionnaire (not in scope for this project) | N/a | Data saved directly to cloud hosted database connected to Analytics Tool (not in scope for this project) | As above | As above
Notes: Please track changes here

## Slide 9: High-level user stories
Success Criteria | Req ID | Story
SC01 | 1.1 | As a programme participant, I want to submit documents electronically to WSF so that I can complete the pre-planning stage of the programme (unit 4)
 | 1.2 | As a programme participant, I want to submit documents electronically to WSF so that I can complete the project evaluation stage of the programme (unit 5)
 | 1.3 | As a WSF team member I want quantitative data that has been submitted by a programme participant to be processed so that I can analyse and report on the data with minimal manual manipulation
 | 1.4 | As a WSF team member I want qualitative data that has been submitted by a programme participant to be processed so that I can analyse and report on the data with minimal manual manipulation
SC02 | 2.1 | As a WSF team member I want all data submitted by programme participants to be structured so that I am able to undertake exploratory data analysis
 | 2.2 | As a WSF team member, I want to build queries from multiple data sources
 | 2.3 | As a WSF team member, I want to define a data sets so that I can perform multivariate analysis on all data (e.g. bar charts or box plots)
 | 2.4 | As a WSF team member, I want to define a data sets so that I can perform multivariate analysis on all data (e.g. create 2 dimensional scatter plots)
SC03 | 3.1 | As a WSF team member, I want to generate charts so that I can visualise the results of a query
 | 3.2 | As a WSF team member, I want to share the outputs of data analysis externally
SC04 | 4.1 | As a WSF team member I want to capture pre and post course data so that I can undertake comparative analysis and track key metrics
Notes: Please track changes here

## Slide 10: Revision History
Document management
Date | Version | Change Description | Name
29th July 2020 | 0.1 | Draft circulated for review | Peter Jefferies
06th Aug 2020 | 0.2 | Updated following review with WSF | Peter Jefferies
Document Change Control
In order to ensure quality and accuracy this document has undergone a number of formal and informal reviews. Feedback and details of any subsequent changes have been captured and can be viewed via the embedded spreadsheet
Notes: Please track changes here

## Slide 11
Appendix A - References
https://en.wikipedia.org/wiki/Exploratory_data_analysis
https://en.wikipedia.org/wiki/Mindset
http://www.winningscotlandfoundation.org/what-we-do/our-work/mindset-in-education/?id=1814
https://chartio.com/docs/visual-sql/
Notes: Please track changes here